## EXAMPLE - RACI Matrix
Project RACI Matrix Template Example |  |  |  | https://www.smartsheet.com/try-it?trp=11440&utm_source=template-google-sheet&utm_medium=content&utm_campaign=Project+RACI+Matrix-google-sheet-11440&lpa=Project+RACI+Matrix+google-sheet+11440
|  |  | Project Sponsor | CPO | Director | Role 4 | Role 5 | Project Manager | Operations Engineer | Quality Assurance | Developer | Role 5 | Consultant | Customer Service | Role 3 | Role 4 | Role 5 | Role 1 | Role 2 | Role 3 | Role 4 | Role 5
PRIORITY | STATUS | PROJECT DELIVERABLE / ACTIVITY | Project Leadership |  |  |  |  | Project Team Members |  |  |  |  | Additional Resources |  | Role 1: Other
PHASE 1
Low | In Progress | Request Review by PMO |  | R |  |  |  | R | A |  | C
Medium | Complete | Submit Project Request | [5 empty] | R | bar: Role 2
High | Needs Review | Research Solution | I |  |  |  |  | A | A | A | C | bar: Role 3; Role 1
| Approved | Develop Business Case | [5 empty] | R | bar: Role 2
Not Started
Overdue
On Hold
PHASE 2
|  | Create Project Charter | C | C |  |  |  | R | C | C | C | bar: Role 3; Role 1
|  | Create Schedule | I | I | I | I |  | R | C | C | C | C | C | C | bar: Role 3; Role 1 to Role 2
|  | Create Additional Plans as Required | I | I | I |  |  | R |  |  |  | I | I | I | bar: Role 3; Role 1 to Role 2
PHASE 3
|  | Build Deliverables | C | C | C | C |  |  | R | R | R | R | A | bar: Role 1
|  | Create Status Report | I | I | I | I |  | A | A | A | A | bar: Role 1 to Role 2
PHASE 4
|  | Perform Change Management |  | C | C | C |  | R | A | A | A | bar: Role 1 to Role 2
PHASE 5
|  | Create Lessons Learned | C | C | C | C |  | R | C | C | C | C | C | C | bar: Role 3; Role 1 to Role 2
|  | Create Project Closure Report | I | I | I | I |  | A | I | I | I | I | I | I | bar: Role 3; Role 2
CLICK HERE TO CREATE IN SMARTSHEET
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## BLANK - RACI Matrix
Project RACI Matrix Template
|  |  | Project Sponsor | CPO | Director | Role 4 | Role 5 | Project Manager | Operations Engineer | Quality Assurance | Developer | Role 5 | Consultant | Customer Service | Role 3 | Role 4 | Role 5 | Role 1 | Role 2 | Role 3 | Role 4 | Role 5
PRIORITY | STATUS | PROJECT DELIVERABLE / ACTIVITY | Project Leadership |  |  |  |  | Project Team Members |  |  |  |  | Additional Resources |  | Role 1: Other
PHASE 1
Low | Complete |  | R
Medium | In Progress |  |  | A
High | Needs Review |  |  |  | C
| Approved |  |  |  |  | I
Not Started
Overdue
On Hold
PHASE 2
PHASE 3
PHASE 4
PHASE 5
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## Dropdown Keys - Do Not Delete -
RACI DROPDOWN KEYS
– DO NOT DELETE –
| RACI KEY | PRIORITY | STATUS
R | Responsible | Low | Not Started
A | Accountable | Medium | In Progress
C | Consulted | High | Complete
I | Informed |  | Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.