## EXAMPLE Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART | [60 empty] | https://goo.gl/ejIdKR
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation |  | 309 | 309 | 0 |  |  |  |  | 100%
1.1 | Project Charter | Leon W | 40 | 40 | 0 |  | 2017-03-12 | 2017-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Project Charter Revisions | Kylie R | 25 | 25 | 0 |  | 2017-03-15 | 2017-03-16 | 2 | 100%
1.2 | Research | Pete S | 100 | 100 | 0 |  | 2017-03-15 | 2017-03-21 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.3 | Projections | Steve L | 60 | 60 | 0 |  | 2017-03-16 | 2017-03-22 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.4 | Stakeholders | Allen W | 40 | 40 | 0 |  | 2017-03-17 | 2017-03-22 | 6 | 100% | bar: WEEK 2 M to WEEK 3 R
1.5 | Guidelines | Malik M | 32 | 32 | 0 |  | 2017-03-18 | 2017-03-22 | 5 | 100% | bar: WEEK 2 M to WEEK 3 R
1.6 | Project Initiation | Malik M | 12 | 12 | 0 |  | 2017-03-23 | 2017-03-23 | 1 | 100% | bar: WEEK 3 F
2 | Project Definition and Planning |  | 210 | 110 | 100 |  |  |  |  | 52.38%
2.1 | Scope and Goal Setting | Steve L | 80 | 70 | 10 |  | 2017-03-24 | 2017-03-28 | 5 | 87.5% | bar: WEEK 4 M to WEEK 5 F
2.2 | Budget | Allen W | 60 | 40 | 20 |  | 2017-03-29 | 2017-04-02 | 5 | 66.67%
2.3 | Communication Plan | Malik M | 40 | 0 | 40 |  |  |  | 1 | 0%
2.4 | Risk Management | Malik M | 30 | 0 | 30 |  |  |  | 1 | 0%
3 | Project Launch and Execution |  | 66 | 0 | 66 |  |  |  |  | 0%
3.1 | Status and Tracking | Pete S | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2 | KPIs | Leon W | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2.1 | Monitoring | Kylie R | 8 | 0 | 8 |  |  |  | 1 | 0%
3.2.2 | Forecasts | Kylie R | 12 | 0 | 12 |  |  |  | 1 | 0%
3.3 | Project Updates | Pete S | 4 | 0 | 4 |  |  |  | 1 | 0%
3.3.1 | Chart Updates | Malik M | 2 | 0 | 2 |  |  |  | 1 | 0%
4 | Project Performance/Monitoring |  | 32 | 0 | 32 |  |  |  |  | 0%
4.1 | Project Objectives | Steve L | 8 | 0 | 8 |  |  |  | 1 | 0%
4.2 | Quality Deliverables | Allen W | 12 | 0 | 12 |  |  |  | 1 | 0%
4.3 | Effort and Cost Tracking | Malik M | 8 | 0 | 8 |  |  |  | 1 | 0%
4.4 | Project Performance | Malik M | 4 | 0 | 4 |  |  |  | 1 | 0%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 617 | 419 | 198 | 60 | 10.2833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 617 | 606.7167 | 596.4333 | 586.15 | 575.8667 | 565.5833 | 555.3 | 545.0167 | 534.7333 | 524.45 | 514.1667 | 503.8833 | 493.6 | 483.3167 | 473.0333 | 462.75 | 452.4667 | 442.1833 | 431.9 | 421.6167 | 411.3333 | 401.05 | 390.7667 | 380.4833 | 370.2 | 359.9167 | 349.6333 | 339.35 | 329.0667 | 318.7833 | 308.5 | 298.2167 | 287.9333 | 277.65 | 267.3667 | 257.0833 | 246.8 | 236.5167 | 226.2333 | 215.95 | 205.6667 | 195.3833 | 185.1 | 174.8167 | 164.5333 | 154.25 | 143.9667 | 133.6833 | 123.4 | 113.1167 | 102.8333 | 92.55 | 82.2667 | 71.9833 | 61.7 | 51.4167 | 41.1333 | 30.85 | 20.5667 | 10.2833
[10 empty] | ESTIMATE | 617 | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15968
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15549
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 |  |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
1.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0! | bar: WEEK 1 M
1.1.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
1.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
1.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
1.4 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
1.5 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
1.6 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
2 |  |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
2.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0! | bar: WEEK 4 M
2.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
2.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
2.4 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3 |  |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
3.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0! | bar: WEEK 7 M
3.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.2.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.2.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.3.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4 |  |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
4.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0! | bar: WEEK 10 M
4.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.4 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 0 | 0 | 0 | 60 | 0 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | ESTIMATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | [60 empty] | 0
[10 empty] | HRS REMAINING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
[6 empty] | 1 | Not Started |  | Not Started | 1
[6 empty] | 2 | In Progress |  | In Progress | 2
[6 empty] | 8 | Completed |  | Completed | 4
[6 empty] | 8 | Not Started |  |  | 8
[6 empty] | 4 |  |  |  | 16
[6 empty] | 80 |  |  |  | 24
[6 empty] | 16 |  |  |  | 40
[6 empty] | 8 |  |  |  | 80
4
2
24
40
8

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED